## INDEX
VISIONNOVA INTERNATIONAL — JIRA PROJECT BACKLOG | Global Optical E-Commerce Platform ¦ 2026–2027
Document Version | v1.0 ¦ Generated 2026-01-15
Total Epics | 18 Epics
Total Stories | 32 User Stories
Total Tasks | 28 Technical Tasks
Total Tickets (All Types) | 78 Tickets
Target Launch | Month 5: Soft Launch (India, UAE, UK) ¦ Month 7: Full Global Launch
SHEET | DESCRIPTION
1. INDEX | This cover sheet with project summary
2. Jira Backlog | Complete master backlog: All Epics, Stories, Tasks with full Jira fields
3. Epics Summary | 18 Epics overview with phase, owner, story count, total story points
4. Sprint Plan | 5-sprint plan + Soft Launch + Full Launch schedule
5. KPI Targets | 15 Year 1 KPIs with targets, benchmarks, owners, and tracking methods

## Jira Backlog
EP-001 | Epic | In Progress - Done |  |  | Platform Foundation & Architecture | Epic: Platform Foundation & Architecture |  |  | Critical | 0 | To Do | Team Lead | PM | Sprint 1 | Infrastructure, Setup | VN-Platform | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-002 | Epic |  |  |  | Homepage & Landing Experience | Epic: Homepage & Landing Experience |  |  | High | 0 | To Do | Team Lead | PM | Sprint 1 | Frontend, Homepage | VN-Frontend | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-003 | Epic |  |  |  | Product Catalog & Search | Epic: Product Catalog & Search |  |  | High | 0 | To Do | Team Lead | PM | Sprint 1 | Catalog, Search, Filter | VN-Catalog | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-004 | Epic |  |  |  | Product Detail & Customization | Epic: Product Detail & Customization |  |  | High | 0 | To Do | Team Lead | PM | Sprint 1 | PDP, Lenses | VN-PDP | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-005 | Epic |  |  |  | AI Virtual Try-On | Epic: AI Virtual Try-On |  |  | High | 0 | To Do | Team Lead | PM | Sprint 1 | AI, AR, Try-On | VN-AI | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-006 | Epic |  |  |  | Teleoptometry & Eye Care Module | Epic: Teleoptometry & Eye Care Module |  |  | Critical | 0 | To Do | Team Lead | PM | Sprint 1 | Teleoptometry, Eye Care | VN-EyeCare | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-007 | Epic | To do- Done |  |  | User Authentication & Accounts | Epic: User Authentication & Accounts |  |  | Critical | 0 | To Do | Team Lead | PM | Sprint 1 | Auth, User, Security | VN-Auth | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-008 | Epic | To do- In Progress |  |  | Prescription Upload & Verification | Epic: Prescription Upload & Verification |  |  | Critical | 0 | To Do | Team Lead | PM | Sprint 1 | Prescription, Compliance | VN-Prescription | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-009 | Epic | To do- In Progress |  |  | Checkout & Payment Gateway | Epic: Checkout & Payment Gateway |  |  | Critical | 0 | To Do | Team Lead | PM | Sprint 1 | Checkout, Payment | VN-Checkout | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-010 | Epic |  |  |  | Order Management & Tracking | Epic: Order Management & Tracking |  |  | High | 0 | To Do | Team Lead | PM | Sprint 1 | Orders, Logistics | VN-Orders | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-011 | Epic |  |  |  | Vision Club Subscription & Loyalty | Epic: Vision Club Subscription & Loyalty |  |  | Medium | 0 | To Do | Team Lead | PM | Sprint 1 | Subscription, Loyalty | VN-Club | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-012 | Epic |  |  |  | Multilingual & Multicurrency | Epic: Multilingual & Multicurrency |  |  | Critical | 0 | To Do | Team Lead | PM | Sprint 1 | i18n, l10n, Currency | VN-Intl | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-013 | Epic |  |  |  | Marketing & Social Impact | Epic: Marketing & Social Impact |  |  | Medium | 0 | To Do | Team Lead | PM | Sprint 1 | Marketing, CSR, Blog | VN-Marketing | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-014 | Epic |  |  |  | Mobile App (iOS & Android) | Epic: Mobile App (iOS & Android) |  |  | High | 0 | To Do | Team Lead | PM | Sprint 1 | Mobile, iOS, Android | VN-App | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-015 | Epic |  |  |  | Admin Panel & Operations | Epic: Admin Panel & Operations |  |  | High | 0 | To Do | Team Lead | PM | Sprint 1 | Admin, Operations, CRM | VN-Admin | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-016 | Epic |  |  |  | Performance, SEO & Accessibility | Epic: Performance, SEO & Accessibility |  |  | High | 0 | To Do | Team Lead | PM | Sprint 1 | SEO, Performance, WCAG | VN-Tech | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-017 | Epic |  |  |  | Customer Support & Help Center | Epic: Customer Support & Help Center |  |  | Medium | 0 | To Do | Team Lead | PM | Sprint 1 | Support, CX | VN-Support | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
EP-018 | Epic |  |  |  | Analytics & KPI Dashboard | Epic: Analytics & KPI Dashboard |  |  | Medium | 0 | To Do | Team Lead | PM | Sprint 1 | Analytics, Reporting | VN-Analytics | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
Ticket ID | Issue Type |  | Epic Link | Epic Name | Story Link | Summary / Title | Description | Acceptance Criteria | Priority | Story Points | Status | Assignee | Reporter | Sprint | Labels / Tags | Components | Module | % Done | Linked Issues | Dependencies | Notes / Comments | Created Date | Due Date
EP-001 | Epic | In Progress - Done |  |  | Platform Foundation & Architecture | Epic: Platform Foundation & Architecture |  |  | Critical | 0 | To Do | Team Lead | PM | Sprint 1 | Infrastructure, Setup | VN-Platform | Platform | 0 |  |  |  | 2026-01-15 | 2026-12-31
ST-001 | Story | Done | EP-001 | Platform Foundation & Architecture |  | Tech Stack Selection & Environment Setup | As a DevOps engineer, I need to finalize the technology stack (frontend, backend, database, CDN, hosting) to set up the development environment. | Tech stack document approved. Dev/staging/prod environments provisioned. CI/CD pipeline live. CDN via Cloudflare configured. | Critical | 13 | To Do | DevOps Lead | CTO | Sprint 1 | Infrastructure, DevOps | Backend | Platform Foundation | 0 |  |  | Tech stack decision needed before any other task | 2026-01-15 | 2026-01-31
TK-001 | Task | Done | EP-001 | Platform Foundation & Architecture | ST-001 | Select and document technology stack | Evaluate and finalize: Frontend (React/Next.js), Backend (Node.js/Python), DB (PostgreSQL + Redis), CDN (Cloudflare), Hosting (AWS/GCP). | Tech stack doc signed off by CTO. No open blockers. | Critical | 5 | To Do | Senior Architect | CTO | Sprint 1 | Infrastructure | Backend | Platform Foundation | 0 |  |  |  | 2026-01-15 | 2026-01-20
TK-002 | Task | Done | EP-001 | Platform Foundation & Architecture | ST-001 | Set up CI/CD pipeline (GitHub Actions / Jenkins) | Configure automated build, test, and deploy pipelines for all environments. | PRs auto-deploy to staging. Main branch deploys to production after approval. | High | 5 | To Do | DevOps Engineer | DevOps Lead | Sprint 1 | CI/CD, DevOps | Backend | Platform Foundation | 0 | TK-001 | TK-001 |  | 2026-01-20 | 2026-01-28
TK-003 | Task |  | EP-001 | Platform Foundation & Architecture | ST-001 | Cloudflare CDN and SSL configuration | Set up Cloudflare CDN for global static asset delivery. Enable SSL, WAF, DDoS protection. | Page load < 2.5s globally. SSL A+ rating. CDN cache hit rate > 90%. | Critical | 3 | To Do | DevOps Engineer | DevOps Lead | Sprint 1 | CDN, Security | Backend | Platform Foundation | 0 |  |  |  | 2026-01-22 | 2026-01-28
ST-002 | Story | Done | EP-001 | Platform Foundation & Architecture |  | Database Schema Design & Setup | As an architect, I need to design and implement the core database schema for products, users, orders, prescriptions, and subscriptions. | ER diagram approved. All core tables created. Indexes optimized. Migration scripts ready. | Critical | 13 | To Do | DB Architect | CTO | Sprint 1 | Database | Backend | Platform Foundation | 0 |  |  |  | 2026-01-15 | 2026-02-05
ST-003 | Story |  | EP-002 | Homepage & Landing Experience |  | Hero Section Implementation | As a visitor, I want to see a compelling hero section that clearly communicates value in 3 seconds so I know this platform is right for me. | Hero loads in < 1.5s. All 3 CTAs functional. Language toggle visible. Hero displays correctly on mobile (70%+ traffic). A/B test variant ready. | High | 8 | To Do | Frontend Dev | Frontend Lead | Sprint 2 | Frontend, UI | Frontend | Homepage | 0 |  | EP-001 |  | 2026-02-01 | 2026-02-14
TK-004 | Task |  | EP-002 | Homepage & Landing Experience | ST-003 | Develop Hero Banner component (React/Next.js) | Build responsive hero with primary headline, sub-headline, dual CTA buttons, trust badges, and hero visual. Implement language toggle. | Component renders correctly on mobile, tablet, desktop. CTAs link to correct pages. | High | 5 | To Do | Frontend Dev | Frontend Lead | Sprint 2 | Frontend | Frontend | Homepage | 0 |  | ST-002 |  | 2026-02-01 | 2026-02-08
TK-005 | Task |  | EP-002 | Homepage & Landing Experience | ST-003 | Implement geo-targeted content display | Auto-detect visitor country/language and display localized hero content, currency, and testimonials. | Geo-detection accuracy > 95%. Fallback to English/USD if detection fails. | High | 3 | To Do | Backend Dev | Backend Lead | Sprint 2 | i18n, Geolocation | Backend | Homepage | 0 |  | TK-004 |  | 2026-02-05 | 2026-02-12
ST-004 | Story |  | EP-002 | Homepage & Landing Experience |  | 3-Tier Product Showcase Section | As a visitor, I want to see all three product tiers clearly so I can find options matching my budget. | All 3 tiers displayed with correct price ranges, taglines, and CTAs. Responsive on all devices. | High | 5 | To Do | Frontend Dev | Frontend Lead | Sprint 2 | Frontend, UI | Frontend | Homepage | 0 |  | ST-003 |  | 2026-02-10 | 2026-02-18
ST-005 | Story |  | EP-002 | Homepage & Landing Experience |  | Social Impact Section & Live Counter | As a visitor, I want to see the Give-Back counter so I feel motivated to purchase for a cause. | Counter updates in real-time from DB. Section visible above the fold on mobile. Shares correctly on social. | Medium | 5 | To Do | Frontend Dev | PM | Sprint 3 | Frontend, CSR | Frontend | Homepage | 0 |  |  |  | 2026-02-15 | 2026-02-25
ST-006 | Story |  | EP-003 | Product Catalog & Search |  | Smart Filter & Sort System | As a shopper, I want to filter products by gender, price, frame shape, material, prescription type, and country so I can find exactly what I need. | All 10 filter types functional. Filter state persists in URL. Results update without full page reload. Performance < 300ms filter response. | High | 13 | To Do | Frontend Dev | Frontend Lead | Sprint 2 | Catalog, Filter, Search | Frontend | Catalog | 0 |  | EP-001 |  | 2026-02-01 | 2026-02-20
TK-006 | Task |  | EP-003 | Product Catalog & Search | ST-006 | Build filter sidebar component with all 10 filter types | Implement: Gender, Age Group, Frame Shape, Frame Material, Lens Type, Price Range (slider), Brand, Color swatches, Country Bestseller, Prescription Type. | All filters render. Multi-select works. Clear all button resets filters. URL reflects filter state. | High | 8 | To Do | Frontend Dev | Frontend Lead | Sprint 2 | Frontend, Filter | Frontend | Catalog | 0 |  |  |  | 2026-02-01 | 2026-02-12
TK-007 | Task |  | EP-003 | Product Catalog & Search | ST-006 | Build sort options dropdown and product grid | Sort by: Price Low-to-High, New Arrivals, Best Seller, Customer Rating, Most Reviewed. | Sort changes product order. Sort state reflected in URL. Grid shows correct currency per visitor. | High | 5 | To Do | Frontend Dev | Frontend Lead | Sprint 2 | Frontend, Catalog | Frontend | Catalog | 0 | TK-006 | TK-006 |  | 2026-02-05 | 2026-02-15
TK-008 | Task |  | EP-003 | Product Catalog & Search | ST-006 | Implement Quick View hover panel | On product card hover: show color variants, price, star rating, Add to Cart and Add to Wishlist buttons. | Quick View appears on hover (desktop) / tap (mobile). Cart action works without page reload. | Medium | 3 | To Do | Frontend Dev | Frontend Lead | Sprint 2 | Frontend, UX | Frontend | Catalog | 0 | TK-007 |  |  | 2026-02-12 | 2026-02-18
ST-007 | Story |  | EP-003 | Product Catalog & Search |  | Global Search with AI-Powered Suggestions | As a shopper, I want to search by voice, text, or style description so I can find products even if I don't know the exact name. | Search results < 500ms. Voice search works on mobile Chrome/Safari. Autocomplete shows after 2 chars. AI style search returns relevant results. | High | 13 | To Do | Backend Dev | Backend Lead | Sprint 3 | Search, AI | Backend | Catalog | 0 |  | EP-005 |  | 2026-02-20 | 2026-03-10
ST-008 | Story |  | EP-004 | Product Detail & Customization |  | Product Detail Page – Core Build | As a shopper, I want to see full product details, choose my prescription type and lens upgrades, and understand delivery timeline before buying. | Page loads < 2s. All 6 image angles present. Prescription selector calculates price correctly. Delivery estimate geo-targeted. Mobile-optimized. | High | 13 | To Do | Frontend Dev | Frontend Lead | Sprint 2 | PDP, Frontend | Frontend | Product Detail | 0 |  | ST-006 |  | 2026-02-01 | 2026-02-22
TK-009 | Task |  | EP-004 | Product Detail & Customization | ST-008 | Build image gallery with 360° view capability | 6-image gallery: front, side, 3/4 angle, on-face (diverse models), close-up. Include 360° view and zoom. | Gallery fully functional on mobile/desktop. Lazy loading implemented. 360° view works on all browsers. | High | 5 | To Do | Frontend Dev | Frontend Lead | Sprint 2 | Frontend, UX | Frontend | Product Detail | 0 |  |  |  | 2026-02-01 | 2026-02-10
TK-010 | Task |  | EP-004 | Product Detail & Customization | ST-008 | Prescription selector & lens upgrade price calculator | Dropdown: Non-Rx / Single Vision / Bifocal / Progressive. Each lens type adds to base frame price. Upgrade checkboxes: Anti-glare, UV400, Blue Light Block, Photochromic, Tinted. | Price updates instantly on selection. Total price shown prominently. Calculation correct for all combinations. | Critical | 8 | To Do | Frontend Dev | Frontend Lead | Sprint 2 | PDP, Pricing | Frontend | Product Detail | 0 | TK-009 |  |  | 2026-02-05 | 2026-02-18
TK-011 | Task |  | EP-004 | Product Detail & Customization | ST-008 | Geo-targeted delivery estimate widget | Auto-detect or use shipping address to show: 'Delivered to [City, Country] by [Date Range]'. Pull real-time data from logistics API. | Delivery estimate accurate for all Phase 1 shipping zones. Fallback message for unsupported regions. | High | 5 | To Do | Backend Dev | Backend Lead | Sprint 2 | Logistics, Geo | Backend | Product Detail | 0 |  | TK-010 |  | 2026-02-10 | 2026-02-20
ST-009 | Story |  | EP-004 | Product Detail & Customization |  | Customer Reviews & Q&A System | As a shopper, I want to read verified reviews filtered by country and face shape to build trust before buying. | Reviews filterable by country, face shape, rating, verified purchase. Q&A answers visible. Photos in reviews render correctly. | Medium | 8 | To Do | Full Stack Dev | Frontend Lead | Sprint 3 | Reviews, Trust | Frontend | Product Detail | 0 |  | ST-008 |  | 2026-02-20 | 2026-03-05
ST-010 | Story |  | EP-005 | AI Virtual Try-On |  | AI Frame Recommender Engine | As a shopper, I want AI to analyze my face shape and lifestyle preferences and suggest the top 5 best frames so I can make a confident choice. | Face shape detection accuracy > 85%. Top 5 recommendations load < 3s. Skin tone analysis functional. Lifestyle preference flow completed. | High | 13 | To Do | ML Engineer | AI Lead | Sprint 3 | AI, ML | AI | Virtual Try-On | 0 |  | EP-001 |  | 2026-02-20 | 2026-03-15
ST-011 | Story |  | EP-005 | AI Virtual Try-On |  | Real-Time AR Try-On Module | As a shopper, I want to try any frame on my live camera feed so I can see exactly how it looks before buying. | AR try-on works on Chrome/Safari mobile and desktop. Face detection triggers in < 2s. Frame swap in < 1s. Share function works. | High | 13 | To Do | AR Developer | AI Lead | Sprint 3 | AR, AI, Frontend | AI | Virtual Try-On | 0 | ST-010 |  |  | 2026-03-01 | 2026-03-20
TK-012 | Task |  | EP-005 | AI Virtual Try-On | ST-011 | Implement AR face landmark detection (MediaPipe/TensorFlow.js) | Use MediaPipe FaceMesh or TensorFlow.js for real-time 468-landmark face tracking on webcam/uploaded photo. | Face detection works on 95% of test devices. Landmark accuracy < 5px error. Works in low-light conditions. | High | 8 | To Do | ML Engineer | AI Lead | Sprint 3 | AR, TensorFlow | AI | Virtual Try-On | 0 |  |  |  | 2026-03-01 | 2026-03-12
TK-013 | Task |  | EP-005 | AI Virtual Try-On | ST-011 | Frame overlay with real-world scale calculation | Calculate interpupillary distance from face landmarks. Map frame dimensions to real-world scale. Overlay frame 3D model on face. | Frame renders at correct scale. No visible Z-fighting. Works on diverse face shapes/skin tones. | High | 8 | To Do | AR Developer | AI Lead | Sprint 3 | AR, 3D | AI | Virtual Try-On | 0 | TK-012 | TK-012 |  | 2026-03-08 | 2026-03-18
ST-012 | Story |  | EP-006 | Teleoptometry & Eye Care Module |  | Teleoptometry Booking System | As a patient, I want to book a video eye test with a certified optometrist in my timezone and language so I can get a prescription without visiting a clinic. | Booking flow < 4 steps. Optometrist availability shown by timezone. Video call link sent within 5 min of booking. Digital prescription stored in vault within 1 hour post-consultation. | Critical | 21 | To Do | Full Stack Dev | Product Lead | Sprint 2 | Teleoptometry, Booking | Backend | Eye Care | 0 |  | EP-007 |  | 2026-02-01 | 2026-03-01
TK-014 | Task |  | EP-006 | Teleoptometry & Eye Care Module | ST-012 | Build optometrist availability calendar & timezone engine | Fetch available optometrists for user's country. Show slots in user's local timezone. Handle DST and cross-timezone bookings. | No double-bookings. Timezone conversions accurate for all 40+ supported countries. Cancellation/rescheduling works. | Critical | 8 | To Do | Backend Dev | Backend Lead | Sprint 2 | Calendar, Timezone | Backend | Eye Care | 0 |  | ST-002 |  | 2026-02-01 | 2026-02-15
TK-015 | Task |  | EP-006 | Teleoptometry & Eye Care Module | ST-012 | Video call integration (Twilio / Daily.co / Zoom SDK) | Integrate HIPAA-compliant video call SDK. Generate unique room per appointment. Send join links via email + SMS + WhatsApp. | Video call joins within 30s. Supports 40+ countries. No data stored beyond session. Encrypted end-to-end. | Critical | 8 | To Do | Backend Dev | Backend Lead | Sprint 2 | Video, HIPAA | Backend | Eye Care | 0 | TK-014 | TK-014 |  | 2026-02-10 | 2026-02-25
TK-016 | Task |  | EP-006 | Teleoptometry & Eye Care Module | ST-012 | Post-consultation digital prescription generation | After call, optometrist fills digital prescription form. System generates PDF prescription. Stores in customer vault. Triggers 'Shop with new prescription' CTA. | Prescription PDF generated < 5 min post-consultation. Stored in customer account. One-click shop redirect works. | Critical | 5 | To Do | Backend Dev | Backend Lead | Sprint 3 | Prescription, CX | Backend | Eye Care | 0 | TK-015 |  |  | 2026-02-20 | 2026-03-05
ST-013 | Story |  | EP-006 | Teleoptometry & Eye Care Module |  | Vision Score Tracker & Prescription Vault | As a patient, I want to track my vision changes over time and store all my prescriptions securely in one place. | Prescription vault stores unlimited prescriptions. Vision score chart shows trends. Reminders sent 11 months after last eye test. | High | 8 | To Do | Full Stack Dev | Product Lead | Sprint 4 | Eye Care, CX | Frontend | Eye Care | 0 |  | ST-012 |  | 2026-03-10 | 2026-03-25
ST-014 | Story | Done | EP-007 | User Authentication & Accounts |  | User Registration & Social Login | As a new user, I want to register quickly via email, phone, or social login so I can start shopping without friction. | Registration < 60s. Email/phone OTP verified. Google, Facebook, Apple login functional. Country + language saved on signup. | Critical | 8 | To Do | Backend Dev | Backend Lead | Sprint 1 | Auth, User | Backend | Auth | 0 |  | EP-001 |  | 2026-01-20 | 2026-02-05
ST-015 | Story | Done | EP-007 | User Authentication & Accounts |  | Customer Portal / My Account Dashboard | As a registered user, I want a dashboard to view my orders, prescriptions, loyalty points, and upcoming appointments. | All order statuses accurate. Prescriptions list shows all uploads. Loyalty points balance correct. Appointments linkable to video call. | High | 13 | To Do | Frontend Dev | Frontend Lead | Sprint 3 | Account, Dashboard | Frontend | Account | 0 |  | ST-014 |  | 2026-02-20 | 2026-03-10
TK-017 | Task |  | EP-007 | User Authentication & Accounts | ST-015 | Build Order History with live status tracking | Display all past and current orders with status: Placed → Lens Cutting → QC → Dispatched → In Transit → Delivered. | Status updates in real-time. Tracking number links to carrier. Lens production video link visible. | High | 5 | To Do | Frontend Dev | Frontend Lead | Sprint 3 | Orders, CX | Frontend | Account | 0 |  | TK-014 |  | 2026-02-20 | 2026-03-01
TK-018 | Task |  | EP-007 | User Authentication & Accounts | ST-015 | Family profile management (up to 5 members) | Allow primary account holder to add up to 5 family members with their own prescriptions and order history. | Family members manageable from single account. Each member has separate prescription vault. Works within Family Club plan. | Medium | 5 | To Do | Full Stack Dev | Product Lead | Sprint 4 | Account, Family | Frontend | Account | 0 |  | ST-014 |  | 2026-03-05 | 2026-03-20
ST-016 | Story | Inprogress | EP-008 | Prescription Upload & Verification |  | AI-Powered Prescription Upload (OCR) | As a customer, I want to upload a photo or PDF of my prescription and have it auto-read so I don't have to type complex values. | OCR reads SPH, CYL, AXIS, ADD, PD with > 90% accuracy. Supports any language, any country format. 4-hour optometrist review SLA met. | Critical | 13 | To Do | ML Engineer | AI Lead | Sprint 2 | OCR, AI, Prescription | AI | Prescription | 0 |  | EP-007 |  | 2026-02-01 | 2026-02-25
TK-019 | Task | Done | EP-008 | Prescription Upload & Verification | ST-016 | Build prescription OCR pipeline (Google Vision / AWS Textract) | Implement OCR to extract prescription fields: SPH, CYL, AXIS, ADD, PD, NV, DV. Handle handwritten and printed formats. | OCR accuracy > 90% on 100-sample test set. Supports: English, Hindi, Arabic, Spanish, French. | Critical | 8 | To Do | ML Engineer | AI Lead | Sprint 2 | OCR, ML | AI | Prescription | 0 |  |  |  | 2026-02-01 | 2026-02-15
TK-020 | Task | Done | EP-008 | Prescription Upload & Verification | ST-016 | Optometrist review queue & verification dashboard | Build internal dashboard for optometrists to review auto-extracted prescriptions, approve or correct, and send confirmation to customer. | Optometrist can review + confirm in < 2 min. SLA alert if review > 4 hours. Discrepancy auto-triggers customer callback. | Critical | 5 | To Do | Full Stack Dev | Product Lead | Sprint 2 | Admin, Prescription | Backend | Prescription | 0 | TK-019 | TK-019 |  | 2026-02-10 | 2026-02-22
ST-017 | Story | Inprogress | EP-009 | Checkout & Payment Gateway |  | Multi-Step Checkout Flow | As a shopper, I want a smooth 3-step checkout (Cart → Address → Payment) with local payment methods and customs duty estimate so I can complete my purchase confidently. | Checkout < 5 min average. Customs duty estimate shown before payment. All regional payment methods functional. Order confirmation via email + SMS + WhatsApp. | Critical | 21 | To Do | Full Stack Dev | Product Lead | Sprint 2 | Checkout, Payment | Backend | Checkout | 0 |  | EP-007 |  | 2026-02-01 | 2026-03-01
TK-021 | Task | Done | EP-009 | Checkout & Payment Gateway | ST-017 | Cart page with prescription confirmation and lens upsell | Show cart items with customization summary. Prompt prescription confirmation. Display lens upgrade upsell panel. Promo code + VN Points redemption. | Promo codes apply correctly. VN Points reduce total. Prescription link visible for each Rx item. | Critical | 8 | To Do | Frontend Dev | Frontend Lead | Sprint 2 | Checkout, Cart | Frontend | Checkout | 0 |  | ST-008 |  | 2026-02-01 | 2026-02-12
TK-022 | Task |  | EP-009 | Checkout & Payment Gateway | ST-017 | International address form with customs duty estimator | Auto-format address fields by country (PIN/ZIP, state, etc.). Show estimated import duties by destination before payment. | Address validation works for all Phase 1 countries. Duty estimate shown for non-free-trade destinations. | Critical | 5 | To Do | Backend Dev | Backend Lead | Sprint 2 | Checkout, International | Backend | Checkout | 0 | TK-021 |  |  | 2026-02-08 | 2026-02-18
TK-023 | Task | Inprogress | EP-009 | Checkout & Payment Gateway | ST-017 | Payment gateway integration – Global & Regional | Integrate: Stripe (global), Razorpay (India), PayPal, Apple Pay, Google Pay. Regional: UPI, GrabPay, M-Pesa, Klarna BNPL, Tabby. | All payment methods tested in sandbox. 3DS authentication works. Payment failures handled gracefully with retry option. | Critical | 13 | To Do | Backend Dev | Backend Lead | Sprint 2 | Payment, Integration | Backend | Checkout | 0 | TK-022 | TK-022 |  | 2026-02-10 | 2026-02-28
ST-018 | Story |  | EP-010 | Order Management & Tracking |  | Real-Time Order Tracking System | As a customer, I want to track my prescription glasses from order placement through lens cutting, QC, dispatch, and delivery with live updates. | Status updates in real-time. Lens production video update sent. Carrier tracking number linked. QR code on package works. | High | 13 | To Do | Full Stack Dev | Product Lead | Sprint 3 | Orders, Logistics | Backend | Orders | 0 |  | EP-009 |  | 2026-02-20 | 2026-03-10
TK-024 | Task |  | EP-010 | Order Management & Tracking | ST-018 | Build order status pipeline (8 states) | Implement: Order Placed → Payment Confirmed → Lens Cutting Started → QC In Progress → Dispatched → In Transit → Out for Delivery → Delivered. Each state triggers customer notification. | Status transitions automated where possible. Manual override available for ops team. All 8 states trigger email + push. | High | 8 | To Do | Backend Dev | Backend Lead | Sprint 3 | Orders, Backend | Backend | Orders | 0 |  | TK-023 |  | 2026-02-20 | 2026-03-05
TK-025 | Task |  | EP-010 | Order Management & Tracking | ST-018 | Carrier API integrations (DHL, FedEx, Aramex, Ninja Van) | Integrate tracking APIs for: DHL, FedEx, Aramex, Ninja Van, J&T Express, DTDC, Delhivery, Royal Mail. | Tracking data syncs every 2 hours. Webhook updates for real-time events. Fallback polling if webhook fails. | High | 8 | To Do | Backend Dev | Backend Lead | Sprint 3 | Logistics, API | Backend | Orders | 0 | TK-024 | TK-024 |  | 2026-02-25 | 2026-03-12
ST-019 | Story |  | EP-011 | Vision Club Subscription & Loyalty |  | Subscription Plan Management | As a member, I want to subscribe to a Vision Club plan and automatically receive discounts, free eye tests, and free frames based on my plan. | All 4 plans functional. Billing auto-renews. Plan benefits apply automatically at checkout. Upgrade/downgrade flow works. | High | 13 | To Do | Full Stack Dev | Product Lead | Sprint 4 | Subscription, Billing | Backend | Vision Club | 0 |  | EP-009 |  | 2026-03-01 | 2026-03-20
ST-020 | Story |  | EP-011 | Vision Club Subscription & Loyalty |  | Loyalty Points Engine | As a shopper, I want to earn and redeem VN Points on every purchase so I feel rewarded for my loyalty. | 1 point per USD 1 earned. 100 points = USD 1 discount. Points visible in cart. Referral USD 10 credit works. Birthday bonus doubles points in birth month. | Medium | 8 | To Do | Backend Dev | Backend Lead | Sprint 4 | Loyalty, Points | Backend | Vision Club | 0 |  | ST-019 |  | 2026-03-10 | 2026-03-25
ST-021 | Story |  | EP-012 | Multilingual & Multicurrency |  | 15-Language Translation Implementation | As a non-English visitor, I want the entire website in my language so I can shop comfortably. | All 15 languages load without broken text. RTL renders correctly (Arabic). Language preference saved in account. URL structure supports language prefixes. | Critical | 21 | To Do | i18n Specialist | Product Lead | Sprint 2 | i18n, l10n | Frontend | International | 0 |  | EP-001 |  | 2026-02-01 | 2026-03-15
TK-026 | Task |  | EP-012 | Multilingual & Multicurrency | ST-021 | Set up i18n framework (next-i18next / react-intl) | Implement i18n library. Create translation JSON files for all 15 languages. Build language switcher component. | All strings externalized. No hardcoded English text. Language switcher changes language without page reload. | Critical | 8 | To Do | Frontend Dev | Frontend Lead | Sprint 2 | i18n | Frontend | International | 0 |  | TK-001 |  | 2026-02-01 | 2026-02-15
TK-027 | Task |  | EP-012 | Multilingual & Multicurrency | ST-021 | Arabic RTL layout implementation | Implement RTL CSS layout for Arabic language. Ensure all components mirror correctly (navigation, tables, forms). | Arabic pages fully RTL. No layout breakage. Tested on Chrome, Safari, Firefox. | Critical | 5 | To Do | Frontend Dev | Frontend Lead | Sprint 3 | Arabic, RTL | Frontend | International | 0 | TK-026 | TK-026 |  | 2026-02-15 | 2026-02-28
ST-022 | Story |  | EP-012 | Multilingual & Multicurrency |  | 50+ Currency Real-Time Conversion | As an international shopper, I want prices shown in my local currency with live exchange rates so I know exactly what I'm paying. | Currency auto-detected from visitor location. 50+ currencies supported. Exchange rates update every hour. Checkout billed in selected currency. | Critical | 8 | To Do | Backend Dev | Backend Lead | Sprint 2 | Currency, Intl | Backend | International | 0 |  | ST-021 |  | 2026-02-10 | 2026-02-28
ST-023 | Story |  | EP-013 | Marketing & Social Impact |  | Blog / Eye Health Hub | As a visitor, I want to read trusted eye health content in my language to educate myself and discover relevant products. | Blog has 3 content pillars. CMS operational. 20 articles published at launch. Author profiles visible. Related products linked. | Medium | 8 | To Do | Content Manager | Marketing Lead | Sprint 4 | Blog, SEO, Content | Frontend | Blog | 0 |  | EP-012 |  | 2026-03-01 | 2026-03-20
ST-024 | Story |  | EP-013 | Marketing & Social Impact |  | Social Impact Dashboard & Give-Back Counter | As a customer, I want to see a live counter of glasses donated and stories of beneficiaries so I feel my purchase matters. | Counter updates from DB after each qualifying order. Map shows beneficiary countries. NGO partner logos link to their sites. | Medium | 5 | To Do | Frontend Dev | PM | Sprint 4 | CSR, Social Impact | Frontend | Social Impact | 0 |  |  |  | 2026-03-10 | 2026-03-25
ST-025 | Story |  | EP-014 | Mobile App (iOS & Android) |  | React Native App Foundation | As a mobile user, I want a native app experience with offline browsing, push notifications, and AR try-on superior to the web version. | App available on iOS App Store + Google Play. Offline catalog works. Push notifications functional. AR frame tracking smoother than web version. | High | 21 | To Do | Mobile Dev | Mobile Lead | Sprint 4 | Mobile, React Native | Mobile | App | 0 |  | EP-001 |  | 2026-03-01 | 2026-04-15
TK-028 | Task |  | EP-014 | Mobile App (iOS & Android) | ST-025 | Barcode scanner for frame compatibility check | Use device camera to scan barcode of any frame. Look up compatible options in VisionNova catalog. Show similar frames. | Scan resolves in < 3s. Compatible frames list accurate. Works on low-light conditions. | Medium | 5 | To Do | Mobile Dev | Mobile Lead | Sprint 5 | Mobile, Scanner | Mobile | App | 0 |  | ST-025 |  | 2026-04-01 | 2026-04-15
ST-026 | Story |  | EP-015 | Admin Panel & Operations |  | Product Catalog Management (CMS) | As an admin, I want to add, edit, and remove products with full details, images, pricing by tier, and shipping availability by country. | CRUD for products operational. Bulk upload via CSV works. Image upload to CDN automated. Product visible on site within 5 min of publish. | High | 13 | To Do | Full Stack Dev | CTO | Sprint 2 | Admin, CMS | Backend | Admin | 0 |  | EP-001 |  | 2026-02-01 | 2026-02-25
ST-027 | Story |  | EP-015 | Admin Panel & Operations |  | Optometrist Network Management | As an admin, I want to onboard, manage, and monitor optometrists across 40+ countries for teleoptometry consultations. | Optometrist profiles with availability, languages, countries. Booking load balanced. Performance ratings visible. Payout tracking. | High | 8 | To Do | Full Stack Dev | Product Lead | Sprint 3 | Admin, Teleoptometry | Backend | Admin | 0 |  | ST-012 |  | 2026-02-20 | 2026-03-10
ST-028 | Story |  | EP-016 | Performance, SEO & Accessibility |  | Core Web Vitals Optimization | As VisionNova, I need the website to achieve Google Page Speed score of 90+ and Core Web Vitals targets to maximize SEO and user retention. | LCP < 2.5s, FID < 100ms, CLS < 0.1. Mobile Page Speed > 90. Desktop > 95. CDN cache hit > 90%. | High | 13 | To Do | Frontend Dev | Tech Lead | Sprint 5 | Performance, SEO | Frontend | Tech | 0 |  | EP-001 |  | 2026-04-01 | 2026-04-30
ST-029 | Story |  | EP-016 | Performance, SEO & Accessibility |  | WCAG 2.1 AA Accessibility Implementation | As VisionNova, we need the website fully accessible for elderly, visually impaired, and screen reader users in all markets. | All pages WCAG 2.1 AA compliant. Screen reader tested (NVDA, VoiceOver). Color-blind mode functional. Voice search works. | High | 13 | To Do | Frontend Dev | UX Lead | Sprint 5 | Accessibility, WCAG | Frontend | Tech | 0 |  |  |  | 2026-04-01 | 2026-04-30
ST-030 | Story |  | EP-017 | Customer Support & Help Center |  | VisionBot AI Chatbot (15 Languages) | As a customer, I want a 24/7 AI chatbot in my language to answer product, prescription, and order questions instantly. | VisionBot handles > 80% of queries without escalation. Response < 3s. All 15 languages functional. Escalation to human agent in < 2 min. | High | 13 | To Do | AI Engineer | Product Lead | Sprint 4 | Chatbot, AI, CX | AI | Support | 0 |  | EP-012 |  | 2026-03-01 | 2026-03-25
ST-031 | Story |  | EP-017 | Customer Support & Help Center |  | Returns & Exchange Management | As a customer, I want to initiate a return or exchange online and receive a pre-paid return label within minutes. | Return request < 3 steps. Pre-paid label generated within 10 min. Refund processed in 3–5 business days. Vision Club instant exchange works. | High | 8 | To Do | Full Stack Dev | Product Lead | Sprint 4 | Returns, CX | Backend | Support | 0 |  | EP-009 |  | 2026-03-01 | 2026-03-20
ST-032 | Story |  | EP-018 | Analytics & KPI Dashboard |  | Executive KPI Dashboard | As a founder, I want to track all Year 1 KPIs (traffic, conversions, AOV, donations, subscriptions) in a real-time dashboard. | All 10 Year 1 KPIs visible. Dashboard updates every 15 min. Export to CSV/PDF. Role-based access (exec vs ops). | Medium | 8 | To Do | Data Engineer | CTO | Sprint 5 | Analytics, BI | Backend | Analytics | 0 |  | EP-009 |  | 2026-04-01 | 2026-04-20

## Epics Summary
Epic ID | Epic Name | Priority | Component | Labels | Status | Sprint | Story Count | Total Story Points | Phase | Owner | Description
EP-001 | Platform Foundation & Architecture | Critical | VN-Platform | Infrastructure, Setup | In Progress | Sprint 1 | 5 | 34 | Phase 1 | CTO | Tech stack, DB schema, CI/CD, CDN, security baseline
EP-002 | Homepage & Landing Experience | High | VN-Frontend | Frontend, Homepage | To Do | Sprint 2 | 4 | 31 | Phase 1 | Frontend Lead | Hero, value strip, carousels, AI try-on entry, social impact
EP-003 | Product Catalog & Search | High | VN-Catalog | Catalog, Search | To Do | Sprint 2 | 3 | 29 | Phase 1 | Frontend Lead | Smart filters, sort, quick view, AI search
EP-004 | Product Detail & Customization | High | VN-PDP | PDP, Lenses | To Do | Sprint 2 | 2 | 34 | Phase 1 | Frontend Lead | Image gallery, Rx selector, lens upgrades, reviews
EP-005 | AI Virtual Try-On | High | VN-AI | AI, AR | To Do | Sprint 3 | 2 | 26 | Phase 1 | AI Lead | Face detection, frame overlay, recommender AI
EP-006 | Teleoptometry & Eye Care Module | Critical | VN-EyeCare | Teleoptometry | To Do | Sprint 2 | 2 | 42 | Phase 1 | Product Lead | Booking, video call, prescription vault, vision tracker
EP-007 | User Authentication & Accounts | Critical | VN-Auth | Auth, User | To Do | Sprint 1 | 2 | 21 | Phase 1 | Backend Lead | Registration, social login, customer portal, family profiles
EP-008 | Prescription Upload & Verification | Critical | VN-Prescription | Prescription | To Do | Sprint 2 | 1 | 21 | Phase 1 | AI Lead | OCR pipeline, optometrist review queue, prescription vault
EP-009 | Checkout & Payment Gateway | Critical | VN-Checkout | Checkout, Payment | To Do | Sprint 2 | 1 | 34 | Phase 1 | Backend Lead | Cart, address, customs duty, all payment methods
EP-010 | Order Management & Tracking | High | VN-Orders | Orders, Logistics | To Do | Sprint 3 | 1 | 21 | Phase 1 | Product Lead | 8-state tracking, carrier APIs, lens production video
EP-011 | Vision Club Subscription & Loyalty | Medium | VN-Club | Subscription | To Do | Sprint 4 | 2 | 21 | Phase 1 | Product Lead | 4 subscription plans, loyalty points engine, referral
EP-012 | Multilingual & Multicurrency | Critical | VN-Intl | i18n, Currency | To Do | Sprint 2 | 2 | 29 | Phase 1 | Product Lead | 15 languages, RTL Arabic, 50+ currencies
EP-013 | Marketing & Social Impact | Medium | VN-Marketing | Marketing, Blog | To Do | Sprint 4 | 2 | 13 | Phase 2 | Marketing Lead | Blog/CMS, social impact dashboard, give-back counter
EP-014 | Mobile App (iOS & Android) | High | VN-App | Mobile | To Do | Sprint 4 | 1 | 26 | Phase 2 | Mobile Lead | React Native, barcode scanner, AR try-on, offline catalog
EP-015 | Admin Panel & Operations | High | VN-Admin | Admin, CMS | To Do | Sprint 2 | 2 | 21 | Phase 1 | CTO | Product CMS, optometrist management
EP-016 | Performance, SEO & Accessibility | High | VN-Tech | SEO, WCAG | To Do | Sprint 5 | 2 | 26 | Phase 2 | Tech Lead | Core Web Vitals, WCAG 2.1 AA, SEO optimization
EP-017 | Customer Support & Help Center | Medium | VN-Support | Support, AI | To Do | Sprint 4 | 2 | 21 | Phase 2 | Product Lead | VisionBot chatbot, returns management
EP-018 | Analytics & KPI Dashboard | Medium | VN-Analytics | Analytics | To Do | Sprint 5 | 1 | 8 | Phase 2 | CTO | Real-time KPI dashboard, Year 1 targets tracking

## Sprint Plan
Sprint | Duration | Focus Areas | Key Deliverables | Total Story Points | Teams Involved | Status
Sprint 1 | Jan 15 – Jan 31 2026 | Platform Foundation, Auth, DB | Tech stack finalized, CI/CD live, DB schema designed, User auth (email + social login) complete, Dev environment ready | 47 | Architecture, Backend, DevOps | In Progress
Sprint 2 | Feb 1 – Mar 1 2026 | Homepage, Catalog, PDP, Checkout, Prescription Upload, Teleoptometry Booking, i18n | Homepage all sections live, Eyeglasses/Sunglasses/Contact Lens catalogs, Product Detail Page, Multi-step Checkout, All Payment Gateways integrated, Prescription OCR live, Teleoptometry booking flow, 15 languages implemented | 180 | Frontend, Backend, AI, i18n | Planned
Sprint 3 | Mar 1 – Mar 25 2026 | AI Try-On, AR, Order Tracking, Search, Post-Consultation | AR Virtual Try-On live, AI Frame Recommender, Real-time order tracking with carrier APIs, Vision Score Tracker, Global AI search | 142 | AI/AR, Backend, Mobile | Planned
Sprint 4 | Apr 1 – Apr 20 2026 | Vision Club, Mobile App, Blog, Social Impact, Support | Vision Club subscription billing live, Loyalty points engine, React Native app submitted to stores, Blog CMS + 20 articles, VisionBot chatbot in 15 languages, Returns management | 113 | Mobile, Product, Content, AI | Planned
Sprint 5 | May 1 – May 31 2026 | Performance, SEO, Accessibility, Analytics | Core Web Vitals 90+ score, WCAG 2.1 AA audit passed, SEO content seeded (2000+ keywords), Executive KPI dashboard, Full QA and security pen test | 55 | Frontend, SEO, Data, QA | Planned
Soft Launch | Month 5–6 (May–Jun 2026) | India, UAE, UK soft launch – limited catalog | 3-market soft launch, bug fixes, payment integration finalization | 0 | All Teams | Planned
Full Launch | Month 7 (Jul 2026) | All Phase 1 markets | 25 markets live, Vision Club active, all 15 languages, PR & influencer push | 0 | All Teams | Planned

## KPI Targets
KPI | Year 1 Target | Industry Benchmark | Measurement Method | Owner | Reporting Frequency | Status
Website Traffic | 3M unique visitors/month by M12 | 1–2M for new e-commerce | Google Analytics + Cloudflare | Marketing Lead | Monthly | On Track
Conversion Rate | 2.8% | 1.5–2% | Orders / Unique Visitors | Product Lead | Weekly | On Track
Monthly Orders | 50,000 orders/month by M12 | Varies by market | Order Management System | Operations | Weekly | On Track
Average Order Value (AOV) | USD 42 blended | USD 35–50 optical | Total Revenue / Total Orders | Finance | Monthly | On Track
Countries Served | 50+ countries with active customers | N/A | Orders by shipping destination | International | Monthly | On Track
Vision Club Members | 100,000 paid subscribers by M12 | N/A (no benchmark) | Subscription Management | Product Lead | Monthly | On Track
Teleoptometry Sessions | 10,000 consultations by M12 | N/A (first mover) | Booking System | Eye Care Lead | Monthly | On Track
Glasses Donated (Social Impact) | 50,000 pairs donated | N/A | NGO partner reports + order count | CSR Lead | Quarterly | On Track
App Downloads | 500,000 iOS + Android downloads | N/A | App Store + Play Store analytics | Mobile Lead | Monthly | On Track
Customer Satisfaction (CSAT) | 4.7+ stars average | 4.2–4.5 optical industry | Review platform aggregation | CX Lead | Weekly | On Track
Bounce Rate (Product Pages) | Under 40% | 55–65% e-commerce average | Google Analytics | Frontend Lead | Weekly | On Track
Virtual Try-On Engagement | 35% of visitors use feature | N/A (unique feature) | Custom event tracking | AI Lead | Weekly | On Track
Cart Abandonment Rate | Under 65% | 70–75% industry average | Checkout funnel analytics | Product Lead | Weekly | On Track
Email Open Rate | 28%+ | 18% optical industry avg | Email marketing platform | Marketing | Weekly | On Track
Page Speed Score | 90+ (Core Web Vitals) | 50–70 average e-commerce | Google PageSpeed Insights | Tech Lead | Monthly | On Track